## Daily Construction Report
Daily Construction Report
Project |  |  |  | Project no. |  |  |  | Report no.
Site address |  |  |  | Date |  |  |  | Day of week
Contractor |  |  |  | Prepared by (name / title) |  |  |  | Contract day no.
WEATHER
Period |  | Temp. (high / low) |  | Conditions |  |  | Wind |  | Work stopped? (hrs / reason)
AM
PM
CREW / LABOR ON SITE
Trade |  |  | Company |  |  | Headcount |  | Hours | Work area
Total | [5 empty] | 0 |  | 0
EQUIPMENT ON SITE
Equipment / unit no. |  |  |  | Owner / rental |  |  | Hours used | Status | Notes
WORK PERFORMED TODAY (BY AREA / ACTIVITY)
MATERIALS DELIVERED
Material |  |  | Quantity |  | Supplier |  |  | Ticket / PO no. |  | Condition / notes
INSPECTIONS / VISITORS
Time | Name / company |  |  | Purpose (inspection, meeting, visit) |  |  |  | Result / follow-up
SAFETY
Today's record
Details of incidents / near misses / corrective actions
DELAYS, ISSUES AND OPEN ITEMS
PHOTOS
Photo 1 | [5 empty] | Photo 2
Insert photo | [5 empty] | Insert photo
Caption | [5 empty] | Caption
GPS / time | [5 empty] | GPS / time
Photo 3 | [5 empty] | Photo 4
Insert photo | [5 empty] | Insert photo
Caption | [5 empty] | Caption
GPS / time | [5 empty] | GPS / time
SIGN-OFF
Prepared by (superintendent) | [5 empty] | Reviewed by (project manager / owner rep.)
Name | [5 empty] | Name
Signature | [5 empty] | Signature
Date | [5 empty] | Date